## JobMonitoring
Month/week | Update JM process
April W3 | "1. Minor & Major changes requested business. 2. Exception Handling/ System/ Managed/ Unmanaged Exceptions. 3. Try Catch Exception management. 4. Making changes in code according to RPA best practices."
April W4 | "1. Dev Testing 2. Problem solving 3. UAT Testing"
May W1 | "1. Solution Redesigned according to requirement 2. Dev testing 3. UAT testing 4. Fixing issues"
May W2 | "1. Fixing Orchestrator issues 2. Dev testing 2. Uat needs to be done"
May W3 | "1. Working on the changes 2. Testing needs to be done for the changes 3. Creating all possible test cases in jira 4. UAT testing is pending "
May W4 | "Working on additional bussiness requirement that are required for jira ticket. Blocker Issue in adding priority and assignee field for jira ticket"
June W1 | "1. Additional business requirements are done. 2. Dev testing is going on . 3. UAT testing pending."
June W2 | Document Prepration for Go live and MHI settlements
Date | Status | Task | Comment
14/06/2021 | MHI Settlement Go Live First Day | Production Testing
15/06/2021 | MHI Settlement Go Live First Day | Production Testing
16/06/2021 | JM process Go live for First time Day 1 | JM hipercare/MhI settlements | Process ran as expected
17/06/2021 | JM process Go live for First time Day 2 | JM hipercare/MhI settlements | Process ran as expected
18/06/2021 | Raised Emergency change request | dev/UAT test | Testing issue
19/06/2021 | week off
20/06/2021
21/06/2021 | Go Live second time Day 1 | UAT Signoff/change request deployment documents | UAT SignOFF
22/06/2021 | Go Live second time Day 2 | hypercare | Process ran as expected
23/06/2021 | Go Live second time Day 3 | hypercare | Process ran as expected
24/06/2021 | Change request 2 | Discussion/dev | Additional BRs
25/06/2021 | Leave
26/06/2021 | week off
27/06/2021
28/06/2021 | Change request 2 | dev
29/06/2021 | Change request 2 | dev
30/06/2021 | Change request 2 | dev/test
2021-01-07 | Change request 2/UAT test signoff | UAT test | UAT SignOFF
2021-02-07 | Change request 2 | change request deployment documents
2021-03-07 | week off
2021-04-07
2021-05-07 | Go Live third time Day 1 | hypercare and went through high level of F-017 P and L Reproting process | Process ran as expected
2021-06-07 | Go Live third time Day 2 | hypercare | Process ran as expected
2021-07-07 | Go Live third time Day 3 | hypercare | Process ran as expected
2021-08-07 | Change request 3 | hypercare/Dev

## ChangeRequests
CR | Details | Reason
Change Request 1 | Process failed to create jira ticket for postponed queues | Never got process in UAT or DEV for Testing
Change Request 2 | Team facing Resolution issue in Jira ticket. Solution provided by Aarthi - Assign jira ticket to user while escalating the jira ticket. | Additional BR
Change Request 2 | Exclusion of some error logs. | Additional BR
Change Request 3 | Create Jira ticket for all error logs of Links2 process | Misinterpretation in BR. | Uat testing is done by Aarthi as well for this case