## TOTAL
RPA Effort Estimation
Phase | Effort (hrs)
Process Analysis | 10
Development | 12
Management | 12
Total: | 34
Disclaimer: This sheet contains aggregated sum of the hours per each category and seniority level.

## ProcessAnalysis
RPA Effort Estimation
Task Name | Effort (hrs) | Buffer (hrs) | Notes
Workshops | 3 | 1
Feasibility check | 3 | 1
Process Standardization | 2 | 1
Process modelling / Diagram | 0 | 0
Process Definition Document | 2 | 1
Disclaimer: This sheet to enter hours related to the process analysis: - Efforts spent on clarifying the process steps with the business users should be booked under "Workshops". - Hours spent on "Process Standardization" topic should be considered whenever business users tend to follow non strict process path, which eventualy need to be narrowed down to a single path. - Fill in "Process modeling/diagram " hours if you use MS Visio or similar tool to represent all the process steps. - "Process Definition Document" a.k.a. PDD is the time needed to describe all process steps along with the respective screenshots.
Note on A4: Adastra: • Observe the entire as-is process, which is ideally presented by the business users. If possible, record a process video. • Identify each process step in detail • Clarify the access requirements for each IT-System • Check that all credentials are available • Check the process maturity: any foreseen changes in the process or the IT systems? • If required, to-dos for standardizing or optimizing the process
Note on A5: Adastra: • Check the feasibility with the development team
Note on A6: Adastra: • Identify the need for standardization or optimization
Note on A7: Adastra: • Model the process with a process diagram
Note on A8: Adastra: • Describe all process-related information and process steps in a PDD • Get a confirmation for the PDD from the business unit members, i.e. process owner

## Development
RPA Effort Estimation
Stage | Task Name | Effort (hrs) | Buffer (hrs) | Notes
Analysis | Feasibility Check | 1
| App familiarization | 0
| Analysis | 1
| Requirements gathering | 1
Technical | Task 1 | 3 | 1
Business logic | Step 1 | 4 | 1
Delivery | Support UAT | 1
| Bug fixes during UAT | 1 | 1
Disclaimer: Development is divided in four major topics: 1. Analysis - Enter all the efforts which your developers will spent on analysing the process before they actually start with the coding. That includes feasibility check, getting familiar with the interface and behaviour of all involved applications, analysing each step of the process and eventually clearing out any additional requirements which might have arose during the aforementioned analysis. 2. Technical - Plan all purely technical tasks which developers are always obliged to execute namely creating and maitaining proper log file, create folder structure and essentially anything else which the has to be in place, but is not stated as a business process step. 3. Business logic - Put the effort needed for each step from the process diagram or the Process Definition Document. 4. Delivery - Plan efforts for supporting the UAT by delivering some test results, as well as fixing any posible bugs found during this time. You should also plan some time for filling in all required project documentation and finaly the hypercare phase when you set your bot on production environment.
Note on A4: Adastra: - all tasks related to development before actually starting with it
Note on B4: Adastra: - is it possible to automate all the process steps? - are there applications which RPA platform cannot handle?
Note on B5: Adastra: - Effort needed by the developer to get acquainted with the interface the of applications, which are part of the process
Note on B6: Adastra: - Initial analysis of the process. Usualy done by reading the PDD and the process diagram
Note on B7: Adastra: - clear out additional requirements which were identified by the developer during the analysis
Note on A8: Adastra: - Any purely technical tasks (ex. logging, inline comments, create folder structure, parametrization etc.)
Note on A13: Adastra: - Any task related to implementing a piece of the business logic. Division can be made based on steps described in the PDD or any other way deemed suitable by the developer
Note on A23: Adastra: - tasks which should happen once the development is done
Note on B23: Adastra: - Load test data for business users
Note on B27: Adastra: - Any effort related to monitoring the automated process after it has been deployed to production environment

## Management
RPA Effort Estimation
Task Name | Effort (hrs) | Buffer (hrs) | Notes
Planning | 2 | 1
Controlling | 2 | 1
Status Updates | 0 | 0
UAT | 4 | 2
Delivery | 4 | 1
Disclaimer: Enter hours related to managing the process automation.
Note on A4: Adastra: • Analyze the required effort and plan the resources for the deployment
Note on A5: Adastra: • During the development, control the status • Budget controlling, i.e. remaining effort vs budget
Note on A6: Adastra: • Present the status of the project to stakeholders
Note on A7: Adastra: • If necessary, set meeting for running the UAT sessions and checking results • Document the UAT phase, i.e. test runs and test cases, and send for confirmation before the deployment
Note on A8: Adastra: • Coordination between relevant units, i.e. development team, IT, business unit

## Metadata (hidden)
Seniority
junior
intermediate
senior